## InProgress
EGS - COMMODITES Automation Status Report | [6 empty] | 2017-08-04
Highlights/Team Notes/Remarks
Current Task List
Module | Sub-Module | Task | Status | Target Completion Date | Progress (Code Complete) | Owner | Issues/Remark
CDBO | CDBO_Deals_PreRequisites | 1. Verify the InBound and OutBound Scheduler of Connex an Grid in Service manger as online | Completed | 2017-08-04 | 100% | Amutha
| CDBO Regression Steps | 1. Ensure the folders are created in local machine to Create Deals 2. Fetch the latest deals in validated status from Endur and export to an excel file 3. Process all the deals passed from Excel except the deals marked as donot process deals flag values. EO-CALL,ENGY-SWAP,EO-ML,EO-P-Dig,EO-PUT,ENGY-SO-P,ENGY-SO-R,EO-CLIQUET,EO-C-Basket,MKT-LINKED-CD,EO-C-Dig,EO-P-Basket,EO-C-FS,COMM-PHYS,ENGY-B-SWAP,COMM-MTLS,COMM-PAL,PWR-SWAP,TR-SWAP 4. Ensure the correct object flag is passed from input sheet 5. Verify the XML is generated for the deals booked and update in excel 6. Booking of Composure with two child deals booked and linked to COM deals and validated. 7. Verify the XML is generated for all the deals of Composure. 8. Verify the status of all deals with xml generated. | Completed
| Deal booking | 1. Process the user list of deals to validate status an update in Excel. 2. Verify the XML is generated for the deals listed. 3. verify the Staus of the deals | Completed | 2017-08-04 | 100% | Amutha
| Veriy the Deals in WOW | 1. For all the deals with XML generated and success status, are validated in WOW. 2. Login to WOW. 3. Verify the Deal has generated the xml in WOW and deal id exist 4. update the status of wow in deal status Excel file. | Inprogress | 2017-08-11 | 75% | Amutha
| Deal booking Sanity Check end to end Work Around to increase the execution speed of Deal booking | 1. verify the InBound and OutBound Scheduler of Connex an Grid in Service manger as online 2. book a single deal with validated status 3. verify the XML is generated and status of the deal 4. send the mail to user with result file 5. Kill the objects at the end and run file in local and copy to the shared path | Inprogress | 2017-08-11 | 75% | Amutha
CR Native Grid workflow. | CR Native Grid workflow PreRequisites | Verify Services Stop and Running Status at Server. Clean up logs and temp files. Verify bat File present in Server. | Completed | 2017-08-02 | 100% | Chaitanya
|  |  | Completed | 2017-08-02 | 100%
| Executing Nativegrid. | Updating Bat file with as of Environment | Completed | 2017-08-02 | 100%
|  | Execute task from two different CMD. | Inprogress | 2017-08-08
| Merging Of Files. | Verify File Generation. | Not Started | 2017-08-11 |  | Chaitanya
Totem | Download Template by runing totem_curve feed from trading manager. | 1) Prerequisite to perform Totem, Creating folder structure, Changing the file name which should not reflect to PROD | Completed | 2017-08-08 | 100% | Swarup
| Template-Daily & Monthly-Oil,USPG,Softs, | Downloading , Pricing, And uploading of templates. | Completed | 2017-08-08 | 100% | Swarup
| Price-Daily-Oil,USPG,Softs and Uploading of template | Validation of file which will get generated by running the task. | Inprogress | 2017-08-08 | 30%
Future Scope
iLTR | TBD | TBD | Awaiting start |  |  |  | Based On Priority From Functional Team Modules need to be Automated.
PNL_Explained | TBD | TBD | Awaiting start
Volcker | TBD | TBD | Awaiting start
B2B | TBD | TBD | Awaiting start
Support Task | TBD | TBD | Awaiting start
Mid-office Task | TBD | TBD | Awaiting start

## Code Complete
EGS - COMMODITES Automation Status Report | [6 empty] | 2017-07-31
Highlights/Team Notes/Remarks
Current Task List
Module | Sub-Module | Task | Status | Code Acceptence | Progress (Code Complete) | Owner | Issues/Remark
Environment Sanity | Env setup and Checks | 1. Ensure the Business,Trading and Operation date all reflect the refresh date. 2. Ensure Raw window/reval screen has data for the refresh date. 3. Price a deal to check if all the tables are populated from Prod during refresh. 4. Run EODMINCUM for one trade to check if configuration is correctly set and save it. 5.Backup the original(Prod) MarketVaRSim\ MarketStressSim\ CreditSim\ Eod_min_cum\ MarketVaRSimIntraday simulation like Creditsim_Orig_Reg16.6 6. Fire select * from vol_data in oracle DB in both UAT2 & UAT3 environment to check data exist or not. 7.Verify all the services are online in Server Management tab. | Completed |  | 100% | Chaitanya
MR Var EOD Workflow | MR Var EOD Task. | 1.Setting the dispathers name to their respective jobs. 2.Setting the sequence number if required to their respective jobs. 3.RunEntireWorkFlow. 4.Executing Jobs. 5.Making Job visibile for Tracking. 6.Tracking Running Jobs. 7.Updating Status Through Email. | Completed |  | 100% | Chaitanya
MR Stress EOD Workflow | MR Stress EOD Tasks. | 1.Assigning the services to their respective jobs. 2.Setting the sequence number if required to their respective jobs. 3.RunEntireWorkFlow. 4.Executing Jobs. 5.Making Job visibile for Tracking. 6.Tracking Running Jobs. 7.Updating Status Through Email. | Completed |  | 100% | Chaitanya
Data Compare Utility | Updation Of Data Compare Utility | EOD-Utility Enhanced for Comparision. ExcelFile Comparision Utility for Folder lever Comparion of Pnls Files. | Completed |  | 100% | Chaitanya
CR EOD Workflow | CR EOD Task. | 1.Assigning the services to their respective jobs. 2.Setting the sequence number if required to their respective jobs. 3.RunEntireWorkFlow. 4.Executing Jobs. 5.Making Job visibile for Tracking. 6.Tracking Running Jobs. 7.Updating Status Through Email. | Completed |  | 100% | Chaitanya
CR Database Validation | Data Validation | CR Analysis by Comparing Data from QA,Base and Prod Databases On: Trade_Count RCTradeAnalytics_TradeCount Book_Count RCTradeAnalytics RCTrades_BookWiseCount RCTrades RCTradeNPV RCTradeSettlementRisk RcScenarios | Completed |  | 100% | Chaitanya
EOD Min Cum | Execution of EOD Min Cum workflow. | 1)EOD_VerifyPrerequisites_Jobs 2)EOD_MinCum_RegressionSteps 3)EOD_ReportValidation | Completed |  | 100% | Swarup
EOD_MinCum_MTM | Execution of EOD_MinCum_MTM workflow. | Verifying the pre-requisite Checking Connex status,checkSchedulerStatus Executing the jobs. Tracking of the job, Folder validation | Completed |  | 100% | Swarup
OCC_ReportValidation | W_DeltaByTransReport | verifyOCCFolderCreation Execute Task. TrackRunningJobs Getting Mail with the location | Completed |  | 100% | Swarup